## Sheet1
Agile Product Backlog
Task Name |  |  | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 |  |  | Yes | Yes | High | In Progress | 16 | Yes
Task 0 | As a gym addict, i want to have an application with graphical user interface that provides me with workout instructions and training tips. | Prepare main window
Task 1.0 | As a user I want to be able to register my profile data and find a proper workout. | Enhance UI with Pprofile Data Window. Add Simple Workout Plans. | Yes | Yes | Medium | Complete | 8 | Yes
Task 1.1 | As a user I want to be able to select either if i want to Login or to create a New Account | Add LogIn Dialog, Move CreateProfile to Dialog. User data saved in JSON Files. | Yes | Yes | Medium | Complete | 8 | Yes
Sprint 2 |  |  | Yes | Yes | Medium | In Progress | 40 | Yes
Task 2.0 | As a user i want to be able to select among exercise programs and fitness tips. So that I can find the ones that suits me or I like the most. | Adding RDBMS Support (PostgreSQL). Prepare data and Insert into DB. | Yes | Yes | High | Complete | 10 | Yes
Task 2.1 | As a user i want to learn more before I select among exercise programs and fitness tips. | Enhance UI with Ineractive Workout Window. | Yes | Yes | High | Complete | 10 | Yes
Task 2.2 | As a user I want to be able to start a full subscription. So that i can get full access and explore all my benefits and provisions of this gym application. | Add Subscription functionality wit registration code. (Payment and code acquisition via Bank Account/SMS/Email) | Yes | Yes | High | Complete | 10 | Yes
Task 2.3 | As a user i want to be able to start a full subscription. So that i can get full access and explore all my benefits and provisions of this gym application. | Add Trainers, Tips and Various workout plans. | Yes | Yes | Medium | Not Started | 10 | No
Sprint 3 |  |  | Yes | No | Medium | In Progress | 0 | No
Task 3.0 |  |  | Yes | Yes | Low | Not Started | 0 | Yes
Task 3.1 |  |  | Yes | Yes | Low | Not Started | 0 | Yes
Task 3.2 |  |  | Yes | Yes | Low | Not Started | 0 | Yes

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started