## Sheet1
Task Name | User Story | Product Backlog Item | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | [5 empty] | Complete | 24
Task 0 | As a gym addict, i want to have an application with graphical user interface that provides me with workout instructions and training tips. | Prepare main window | Yes | Yes | High | Complete | 8 | Yes
Task 1.0 | As a user I want to be able to register my profile data and find a proper workout. | Enhance UI with Pprofile Data Window. Add Simple Workout Plans. | Yes | Yes | Medium | Complete | 8 | Yes
Task 1.1 | As a user I want to be able to select either if i want to Login or to create a New Account | Add LogIn Dialog, Move CreateProfile to Dialog. User data saved in JSON Files. | Yes | Yes | Medium | Complete | 8 | Yes
Sprint 2 | [5 empty] | Complete | 40
Task 2.0 | As a user i want to be able to select among exercise programs and fitness tips. So that I can find the ones that suits me or I like the most. | Adding RDBMS Support (PostgreSQL). Prepare data and Insert into DB. | Yes | Yes | High | Complete | 10 | Yes
Task 2.1 | As a user i want to learn more before I select among exercise programs and fitness tips. | Enhance UI with Ineractive Workout Window. | Yes | Yes | High | Complete | 10 | Yes
Task 2.2 | As a user I want to be able to start a full subscription. So that i can get full access and explore all my benefits and provisions of this gym application. | Add Subscription functionality wit registration code. (Payment and code acquisition via Bank Account/SMS/Email) | Yes | Yes | High | Complete | 10 | Yes
Task 2.3 | As a user i want to be able to start a full subscription. So that i can get full access and explore all my benefits and provisions of this gym application. | Add Trainers, Tips and Various workout plans. | Yes | Yes | Medium | Complete | 10 | Yes
Sprint 3 |  | Code Freeze - Refactor |  |  |  | In Progress | 0
Task 3.0 | As a user i would like to get informed about the availability of training sessions in the fitness center. | Add Gym Facilities Schedule. Update status via web services. | Yes | Yes | Low | Not Started | 10 | Yes
Task 3.1 | As a user I want to be able to update my profile, so that my suggested workout can evolve. | Record Somatometric Data, Calculate BMI, Create/Implement algorithms adjust Workout Plan | Yes | Yes | Low | Not Started | 20 | Yes
Task 3.2 | As a user I want to be able to book a training session or a workout and read my coaches tips on their profiles. | Connect to Gym's booking app. | Yes | Yes | Low | Not Started | 10 | Yes